## Trang tính1
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Chain store management system | Design requirements for a chain store management system | 2 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
Actor | Identify and describe the actors (actors/users) in the system. | 3 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
Context Diagram | Draw a context diagram for the system. | 4 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
Screen Description | Write detailed screen descriptions. | 5 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
User Login Screen | Login interface and links for password recovery/registration | 1 |  | Open | ChiHTH |  |  | Iteration 1 | WP, 2_Doing
Write RDS for User Login | Write the Functional Specification Document (FSD) for the Login screen. | 2 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
Write SDS for User Login | Detailed design (SDS – Class, SQL) for the Login screen | 3 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
Write Code for User Login | Implement and write unit tests for the Login screen. | 4 |  | Open | ChiHTH |  |  | Iteration 1 | Task, 2_Doing
Integrate User Login | Integrate the Login screen with other screens. | 5 |  | Open | ChiHTH |  |  | Iteration 1 | Task, 1_To Do
Login | Specification and high-level design for the login function (system) | 6 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done | Login
Forgot Password | Design and develop the "Forgot Password" function. | 8 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done | Forgot Password
Logout | Thiết kế và phát triển chức năng Đăng xuất | 9 |  | Close | ChiHTH |  |  | Iteration 1 | Task, 3_Done
Supplier Manager | Design and build the Supplier Management screen. | 10 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Supplier List
Edit Supplier | Design and develop the "Edit Supplier Information" function. | 11 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Edit Supplier
Search Supplier | Design and development of the supplier search function | 12 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Search Supplier
Filter Supplier | Design and develop the supplier list filtering function. | 13 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Filter Supplier
Paging | Develop pagination functionality for lists (suppliers, etc.) | 14 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Pagging
Income Manager | Design and implement the Income Receipt Management function. | 15 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Cashbook
Expense Manager | Design and implement the Expense Voucher Management function. | 16 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Cashbook
Add Expense | Design and develop the "Create New Expense Interface" feature. | 17 |  | Close | ChiHTH |  |  | Iteration 2 | Task, 3_Done | Add Expense
Lock / Unlock User | Allows administrators to activate or deactivate a user account by changing its status without permanently deleting the account. | 36 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Lock / Unlock User
Loyal Customer Ranking | Displays customers ranked according to loyalty criteria such as accumulated points, purchase frequency, or total spending. | 33 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Loyal Customer Ranking
Customer Detail | Displays detailed information about a selected customer, including profile, purchase history, loyalty points, and account status. | 32 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Customer Detail
Search/Filter Customer | Enables searching and filtering customers by criteria such as name, phone number, email, membership level, or loyalty points. | 31 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Search/Filter Customer
Edit Customer | Allows authorized users to update existing customer information such as contact details, address, and membership information. | 30 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Edit Customer
Add Customer | Provides a form for registering a new customer by entering contact information and other required customer details. | 29 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Add Customer
Customer Manager | Displays a list of customers and provides management functions including adding, editing, searching, filtering, viewing details, and ranking loyal customers. | 28 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Customer Manager
Profile | Displays the logged-in user's personal information and allows them to view or update editable profile details. | 27 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Profile
Employee Sales Report | Displays sales performance statistics for employees, including revenue, completed orders, and other performance metrics within a selected period. | 26 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Employee Sales Report
Search/Filter User | Allows users to search and filter the user list based on criteria such as name, email, phone number, role, or account status. | 25 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Search/Filter User
Edit User | Enables administrators to modify existing user information such as personal details, assigned role, and account status. | 24 |  | Close | DungLD |  |  | Iteration 1 | Task, 3_Done | Edit User
Add User | Provides a form for creating a new user account by entering required personal information, role, and login credentials. | 23 |  | Close | DungLD |  |  | Iteration 1 | Task, 3_Done | Add User
Change Password | Allows the currently logged-in user to securely update their account password after validating the current password and password confirmation. | 22 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Change Password
User Manager | Displays a list of all users with management functions such as searching, filtering, adding, editing, locking/unlocking accounts, and viewing user details. | 21 |  | Close | DungLD |  |  | Iteration 1 | Task, 3_Done | User Manager
Screen Flow | Defines the navigation flow between all screens in the User Management and Customer Management modules, illustrating how users move from one screen to another based on system actions. | 20 |  | Close | DungLD |  |  | Iteration 2 | Task, 3_Done | Screen
Category Manager | Core category management interface providing category listing, product count mapping, status management (Active/Inactive), keyword search, status filtering, soft delete, and server-side SQL pagination. | 37 |  | Close | ThangLV |  |  | Iteration 1 | Task, 3_Done | Category List
Add Category | Modal form interface for creating new product categories with name validation, status selection (Active/Inactive), and description input. | 38 |  | Close | ThangLV |  |  | Iteration 1 | Task, 3_Done | Add Category
Edit Category | Interface and backend logic for updating existing category properties including category name, status, and description. | 39 |  | Close | ThangLV |  |  | Iteration 1 | Task, 3_Done | Edit Category
Delete / Soft Delete Category | Soft delete implementation for categories setting is_deleted status to preserve data integrity and foreign key constraints with linked products. | 40 |  | Close | ThangLV |  |  | Iteration 1 | Task, 3_Done | Delete Category
Search/Filter Category | Real-time keyword search and status filtering (Active/Inactive) with SQL pagination for efficient category management. | 41 |  | Close | ThangLV |  |  | Iteration 1 | Task, 3_Done | Search/Filter Category
Warehouse Manager | Central multi-branch warehouse management dashboard displaying inventory stock levels, KPI summary metrics, low stock alerts, and sub-view tab navigation. | 42 |  | Close | ThangLV |  |  | Iteration 2 | Task, 3_Done | Warehouse Manager
Stock Import Manager | Supplier stock import workflow supporting product batch selection, unit import price schema, total cost calculation, and bulk Excel file import via Apache POI. | 43 |  | Close | ThangLV |  |  | Iteration 2 | Task, 3_Done | Stock Import
Stock Out Manager | Stock out voucher creation and processing for damaged goods, expired items, and inventory returns with automatic stock quantity deduction. | 44 |  | Close | ThangLV |  |  | Iteration 2 | Task, 3_Done | Stock Out
Stock Transfer Manager | Inter-branch warehouse stock transfer workflow supporting origin/destination selection, stock isolation, and multi-state tracking (Pending, In-Transit, Completed, Cancelled). | 45 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Stock Transfer
Stock Approval Workflow | Two-tier approval handshake mechanism where source branch dispatches stock and destination branch verifies and approves receipt to update inventory. | 46 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Pending Approvals
Stock Audit & Inventory Check | Physical inventory audit feature comparing actual physical counts against system stock levels, calculating discrepancies, and generating adjustment vouchers. | 47 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Inventory Check
Stock Transaction History | Transaction log module recording all stock movements (Import, Out, Transfer, Audit) with multi-criteria filtering by date range, voucher type, branch, and keyword. | 48 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Stock History
Low Stock Recommendation | Automated inventory replenishment recommendation algorithm calculating minimum stock thresholds and generating reorder suggestions for store managers. | 49 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Low Stock Report
Printable Stock Voucher | Printable layout templates for stock import, stock out, and transfer receipts featuring delivery partner details, employee info, and itemized cost tables. | 50 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Print Voucher
Warehouse Role & Security Filter | Role-based access control (RBAC) and inter-warehouse data isolation ensuring branch staff can only access inventory vouchers assigned to their specific store. | 51 |  | Close | ThangLV |  |  | Iteration 3 | Task, 3_Done | Security & Access Control